## Plan Information
Plan name | PATVS软件测试(1) | Project name | M410 Mouse
Test type | Manual | Creator | jiangjie6
Version | v1
Workloading(Min) | 2548(Min) | Phase | DVT
Start date | 2024-05-27 | End date | 2024-05-31
OS | Win 11 | Language | EN
Product | M410 Mouse | SKU | M410 SKU1 compatibility(M410 Mouse)
Objective | 软件调试
Description | 软件调试 鼠标FW：v125 dongle FW：v113 软件版本：v1.0.0.1
Plan workloading | Actual workloading | Remain workloading | Done percent
2548(Min) | 0(Min) | 2548(Min) | 0%

## Case List
Category | Case name | Version | Auto type | SKU |  |  | OS | Language | Pass | Fail | Result | Done percent | Tester | Workloading | Planned start | Planned end | Actual start | Actual end
|  |  |  | Product | Name | Quantity
Mouse test case | Mouse Scenario test 01 | V0.4 |  |  |  |  | Win 11 | EN | 0 | 0 |  | 0% | jiangjie6 | 204(Min) | 2024-05-27 | 2024-05-31 | 2024-05-28
Mouse test case | Mouse Basic function t... | V0.7 |  |  |  |  | Win 11 | EN | 0 | 0 |  | 0% | jiangjie6 | 367(Min) | 2024-05-27 | 2024-05-31
Mouse test case | Mouse Scenario test 02 | V0.4 |  |  |  |  | Win 11 | EN | 0 | 0 |  | 0% | jiangjie6 | 434(Min) | 2024-05-27 | 2024-05-31
Mouse test case | Mouse Basic function t... | V0.4 |  |  |  |  | Win 11 | EN | 0 | 0 |  | 0% | jiangjie6 | 399(Min) | 2024-05-27 | 2024-05-31
Mouse test case | Plug test(matrix) | V0.2 |  |  |  |  | Win 11 | EN | 0 | 0 |  | 0% | jiangjie6 | 90(Min) | 2024-05-27 | 2024-05-31
Mouse test case | Mouse Basic function t... | V0.3 |  |  |  |  | Win 11 | EN | 0 | 0 |  | 0% | jiangjie6 | 1054(Min) | 2024-05-27 | 2024-05-31

## 1-Mouse Scenario test 01
Basic:
Case type : | SW | Case ID: | MSA001_01
Case name : | Mouse Scenario test 01 | Category folder : | Mouse test case
Version : | V0.4 | Execution type : | Single
Keywords : | Input | Status : | Active
Auto type :
Workloading : | 204(Min) | OS :
Priority : | High | Phase : | CV,DVT
Creator : | yangbk2 | Owner : | yangbk2
Objective : | To verification Mouse compatibility test | Release notes : | 分行
Type matrix : | Mouse Scenario test 01 | Case tools :
NA | Not support | Block | On going | Not start | Pass | Fail | Total
0 | 0 | 0 | 0 | 48 | 0 | 0 | 48
Comments :
Test case item |  |  |  | Expected result |  | Mouse Scenario test 01
Section : | Preparation (4) |  |  |  |  | Not test
Workloading : | (Min) | Leadingtime : | (Min) | Phase :
Preparation test units and download the latest preload image/driver/BIOS etc.. 记录系统配置及键鼠样品编号FW/HW/SW信息并上传至comments |  |  |  | Expected Result1 |  | Not test
Section : | PowerStressTest (30) |  |  |  |  | Not test
Workloading : | (Min) | Leadingtime : | (Min) | Phase :
Please cover wired and wireless USB mouse and cover each USB port | [5 empty] | Not test
1.Loop Restart
Action 1: Use LAAT to test |  |  |  | -System no hang-up; Unexpected shut down / reboot; Device no lost in Device Manager; No any functional problems; No any physical damages |  | Not test
Action 2: Original way 1. Install Test Program (Mike-II) 2. Attach DUT device to the system 3. Launch Mike-II and click" SYS INFORMATION ".Select the advaned, then click "SET" and close this windows(Please follow attached file) 4.Loop restart/suspend/hibernation test, it requires to test 300 trials. Note: If there's a error come about with the notice whose code is 0xc000007b, please find a DirectX restoring tool to fix the issue. Remark: Statistical Criteria for defect verification: To close the intermittent defect of Loop restart/suspend/hibernation test, it requires to test 600 trials. |  |  |  | -MIKE is running with no error - MIKE displays "PASS" result message after abortion -System no hang-up; Unexpected shut down / reboot; Device no lost in Device Manager; No any functional problems; No any physical damages |  | Not test
2.Loop Suspend
Action 1: Use LAAT to test |  |  |  | -System no hang-up; Unexpected shut down / reboot; Device no lost in Device Manager; No any functional problems; No any physical damages |  | Not test
Action 2: Original way 1. Install Test Program (Mike-II) 2. Attach DUT device to the system 3. Launch Mike-II and click" SYS INFORMATION ".Select the advaned, then click "SET" and close this windows(Please follow attached file) 4.Loop restart/suspend/hibernation test, it requires to test 300 trials. Note: If there's a error come about with the notice whose code is 0xc000007b, please find a DirectX restoring tool to fix the issue. Remark: Statistical Criteria for defect verification: To close the intermittent defect of Loop restart/suspend/hibernation test, it requires to test 600 trials. |  |  |  | -MIKE is running with no error - MIKE displays "PASS" result message after abortion -System no hang-up; Unexpected shut down / reboot; Device no lost in Device Manager; No any functional problems; No any physical damages |  | Not test
3.Loop Hibernation
Action 1: Use LAAT to test |  |  |  | -System no hang-up; Unexpected shut down / reboot; Device no lost in Device Manager; No any functional problems; No any physical damages |  | Not test
Action 2: Original way 1. Install Test Program (Mike-II) 2. Attach DUT device to the system 3. Launch Mike-II and click" SYS INFORMATION ".Select the advaned, then click "SET" and close this windows(Please follow attached file) 4.Loop restart/suspend/hibernation test, it requires to test 300 trials. Note: If there's a error come about with the notice whose code is 0xc000007b, please find a DirectX restoring tool to fix the issue. Remark: Statistical Criteria for defect verification: To close the intermittent defect of Loop restart/suspend/hibernation test, it requires to test 600 trials. |  |  |  | -MIKE is running with no error - MIKE displays "PASS" result message after abortion -System no hang-up; Unexpected shut down / reboot; Device no lost in Device Manager; No any functional problems; No any physical damages |  | Not test
4.Loop Power on/off
Action 1: Use LAAT to test |  |  |  | -System no hang-up; Unexpected shut down / reboot; Device no lost in Device Manager; No any functional problems; No any physical damages |  | Not test
Action 2: Original way 1. Attach DUT to the system 2. Launch Mike-II (Pay attention to the sequence,don't lauch Mike-II without attaching testing device), refer fig1. 3. Power on/off test: Click: "Power Off" 4. After system powered off, press power button to power on the system. 5. Repeat step 4 200 times. |  |  |  | -MIKE is running with no error - MIKE displays "PASS" result message after abortion -System no hang-up; Unexpected shut down / reboot; Device no lost in Device Manager; No any functional problems; No any physical damages |  | Not test
Section : | Plug Test (30) |  |  |  |  | Not test
Workloading : | (Min) | Leadingtime : | (Min) | Phase :
Please cover wired and wireless USB mouse and cover each USB port | [5 empty] | Not test
N5(01)Hot plug in and out N5(DUT side) 热插拔
1. Hot plug DUT with USB device to the system, and check the DUT can be recognized normally 2. unplug USB device from DUT when LED is stable 3. Hot plug usb device to the DUT after 2s, and check the USB device can be reconised normally. For Headset, hot unplug headset during playback audio file by OS bring player, then hot plug in headset 4. Repeat step 1-3 for 5 times,it requires to test all IO port on DUT |  |  |  | No Blue screen No yellow mark in device maNAgement No any window popup No function problem |  | Not test
N5(02) Warm plug in test N5(DUT side) 睡眠插拔
1. Let system enter sleep mode 2.. Plug in DUT with device then wake up system, ensure DUT can be detected and work normally 3. Let system enter sleep mode again 4. Plug out device from DUT then wake up system,ensure system can work normally and no any error message pops 5.Repet above steps 1-4 over 5 times,it requires to test all IO port |  |  |  | No Blue screen No yellow mark in device maNAgement No any window popup No function problem |  | Not test
N5(03)S4 plug in test N5(DUT side) 休眠插拔
1. Let system enter hiberNAtion mode 2.. Plug in DUT with device then wake up system, ensure DUT can be detected and work normally 3. Let system enter hiberNAtion mode again 4. Plug out device from DUT then wake up system,ensure system can work normally and no any error message pops 5.Repet above steps 1-4 over 5 times,it requires to test all IO port |  |  |  | No Blue screen No yellow mark in device maNAgement No any window popup No function problem |  | Not test
N5(04)Cold plug in test N5(DUT side) 冷插拔
1. Let system enter power off mode 2. Plug in device then wake up system, ensure device can be detected and work normally 3. Let system enter poweroff mode again 4. Plug out device from DUT then wake up system,ensure system can work normally and no any error message pops 5.Repet above steps 1-4 over 5 times,it requires to test all USB port for USB device |  |  |  | No Blue screen No yellow mark in device maNAgement No any window popup No function problem |  | Not test
Section : | LED Test (10) |  |  |  |  | Not test
Workloading : | (Min) | Leadingtime : | (Min) | Phase :
Please cover wired and wireless USB mouse and cover each USB port | [5 empty] | Not test
N5(01)LED Light Check LED灯检查
1. Check LED Position 2. Connect power adapter to DUT 3. Connect DUT to system 4. Power on DUT/system 5. Check the LED light and color of DUT |  |  |  | Refer to product spec |  | Not test
N5(02)LED behavior check
（ with a test instrument 1. Connect power adapter to DUT 2. Connect DUT to system 3. Power on DUT/system 4. Check the LED status during system in S0/S3/S4/S5(Such as color and flicker) |  |  |  | Refer to product spec |  | Not test
Section : | WirelessPairingTest (30) |  |  |  |  | Not test
Workloading : | (Min) | Leadingtime : | (Min) | Phase :
Please cover wired and wireless USB mouse and cover each USB port | [5 empty] | Not test
N5(N5）N5(01)2.4G Normal pairing/unpairing 2.4G对码
1.Turn on DUT 2.Connect dongle to system 3.Pairing the dongle 4.Do simple function check |  |  |  | 1.DUTcanbesearched 2.Devicecanbepaired/deleted,anddevicere-pairingsuccess |  | Not test
N5(02)BT Normal pairing/unpairing BT对码
1.Turn on DUT BT pairing mode 2.Search DUT by system 3.Pair the DUT 4.Do simple function check 5.Un pairing the dongle |  |  |  | 1.DUTcanbesearched 2.Devicecanbepaired/deleted,anddevicere-pairingsuccess |  | Not test
N5(03)BT Pairing multi devices BT多设备配对
1.System pairing one or more other BTdevice first 2.Pairing DUT 3.DUT should can be seached by an other system 4.Remove the DUT or disconnect the DUT 5.DUT pairing an other system 6.Repeat step 2-3 10times |  |  |  | 1.DUTcanbesearched 2.Devicecanbepaired/deleted,anddevicere-pairingsuccess |  | Not test
N5(04)2.4G Pairing multi devices 2.4G多设备配对
1.Plug the dongle to the system 2.Pairtwo mouse to the dongle 3.Dosimplefunction check. 4.Change the dongle to different USB portsanddifferentmachine. |  |  |  | 1.Bothmouseshouldbenoabnormal 2.Noneedre-paired |  | Not test
N5(05)2.4G Multi pledongle pairing 多个接收器配对
1.Plug two dongle to differentmachine. 2.Pair mouse to firstm achine.Check basic function. 3.Pair the mouse to second machine,check basic function. |  |  |  | 1.Devicecanpairedseconddongle,nofunctionerror 2.Themouseshouldcancelpairingwiththefirstdongle |  | Not test
N5(06)Pairing memory function 配对是否有保存记忆
1.Pair the mouse to the dongle 2.Move the mouse far away from the dongle (>30cm) and press the pairing button. After 150s the mouse will fail to pair.The yellow light will change to amber. 3.Then the mouse will remember the last pairing. 4.The last pairing should work normally.Check basic function,the mouse should use normally. |  |  |  | 1.Thelastpairingshouldworknormally. 2.Checkbasicfunction,themouseshouldusenormally. |  | Not test
Section : | WirelessReconnectionTest (30) |  |  |  |  | Not test
Workloading : | (Min) | Leadingtime : | (Min) | Phase :
Please cover wired and wireless USB mouse and cover each USB port | [5 empty] | Not test
N5(01)DUT stand by disconnection DUT断开
1.Pair the DUT to the system. Test SceNArio 2(mouse) 3.Idle the DUT for 5 mins . After 5mins, Check the DUT Basic function. 4.Repeat step2-3 for 10 times and check that there should be no connection droping . |  |  |  | 1.There should be no connection droping |  | Not test
N5(02)System stand by disconnection 系统处于断开检查状态
1.Pair the DUT to the system . 2.Power setting options changed to "1min". 3.Wait for 5 mins . Then wake up system, check the DUT Basic function. 4.Repeat step2-3 for 10 times and check that there should be no connection droping . |  |  |  | 1.The DUT can be auto paired |  | Not test
N5(03)Beyond Distance disconnection 与OS配对后，移除范围，再回到范围
1. Pairing DUT with one system 2. Take DUT out of system range 3. Take the DUT back to system range, check the pairing status |  |  |  | 1.The DUT can be auto paired |  | Not test
Section : | WirelessDistanceTest (30) |  |  |  |  | Not test
Workloading : | (Min) | Leadingtime : | (Min) | Phase :
Please cover wired and wireless USB mouse and cover each USB port | [5 empty] | Not test
N5(01)Connection distance 3m/5m/10m 距离测试
1. Connect the DUT with a PC .The distance between PC and DUT is 3m/5m/10m. 2.Do simple function check |  |  |  | 1.No mouse stuck, no garbage 2.Don't drop connection, no mouse delay |  | Not test
N5(02)最大连接距离内鼠标功能测试
1. Connect the DUT with a PC 2.Take the mouse some distance away from the PC and make sure that the mouse is thrown to connect with Dongle |  |  |  | 1.Mouse does not interrupt connection ( conform to specifications ) |  | Not test
N5(03)Remove DUT during system shut downN5(DUT side) 将DUT移除范围，再回到连接范围看是否能回连
1.Attach DUT with device to system and boot into OS. 2.Select Shutdown, perform real shutdown ( Shift key + Shutdown ) 3.Immediately remove device from DUT during shutdown (timing is important if you wait too long after shutdown the condition will not be seen) <- remove in 1 sec. System completes shutdown 4.Power on system,check if system is working normally 5. Repet above steps 1-4 over 5 times,it requires to test all USB port for USB device |  |  |  | Make sure system all function works fine(etc… K/B,track ponit can work normally |  | Not test
Section : | Wireless interference test (30) |  |  |  |  | Not test
Workloading : | (Min) | Leadingtime : | (Min) | Phase :
Please cover wired and wireless USB mouse and cover each USB port | [5 empty] | Not test
N5(01)WIFI Interference test干扰 WIFl 干扰测试
1. Load test system with DUT 2. Place the DUT in proximity of the rounter(distance < 1m). 3. Evaluate the function of the DUT while the rounter is also in use. 4. Record the results in the table below |  |  |  | 1. No stuck 2. No Display garbage 3. No Speaker noise 4. No delay |  | Not test
N5(02)2.4G Interference test干扰 2.4 g干扰测试
1. Preload system with latest OS image and FW/BIOS/ME 2. update dock FW/Driver to latest 3. Connect dock into system with all available device especially Monitors. 4. Connect 2.4G mouse dongle into dock USB port A, (define port A,B... before test) 5. Connect USB key into nearby USB port. (must use metal USB key) 6. Keep mouse away from dock 20/50/100/150 cm and front 0/45/-45 degree (like pic below) 7. Use Areson Mouse test program to test if mouse move any lag. 8. Record the result into attached file table. ---Case 1 9. Unplug USB key from nearby USB port 10. Repeat step 6-8 again. --Case 2 11. Connect 2.4G mouse dongle into dock another USB port (one by one till all USB port been tested) 12. Repeat step 5-10 again. --Case 3. 13. change to another 2.4G mouse and connect to dock (one by one till all 2.4G mouse been tested) 14. Repeat step 4-12 again. --Case 4 15. Record all data into attached file table. | [5 empty] | Not test
Section : | Information check (10) |  |  |  |  | Not test
Workloading : | (Min) | Leadingtime : | (Min) | Phase :
Please cover wired and wireless USB mouse and cover each USB port | [5 empty] | Not test
N5(01)Yellow Mark Check
1.Launch device maNAgement after driver installed 2.Click each Driver item. 3.Check all drivers status. | [5 empty] | Not test
N5(02)Taskbar and Navigation
1.After driver has installed and it show in Taskbar or NAvigation,then Click Taskbar or NAvigation (if not show in Taskbar or NAvigation ,then block) 2.Check the section under 'start screen' in NAvigation tab 3.then apply one by one. | [5 empty] | Not test
N5(03)CPU usage rate check
1.The device is working with driver installed 2.Simulate the end user to use the device 3.Open task maNAger to check the CPU usage rate | [5 empty] | Not test
N5(04)Memory Leakage check
1. Installed driver, connect DUT to system 2. Open Task MaNAger 3. Find the driver/app's process in task maNAger 4. Record down the memory usage of the app/process 5. Unplug and replug DUT 5 times 6. Repeat step 4-5 2 times 7. S3/resume 10 times, then do step 4 8. S4/resume 10 times, then do step 4 9. Restart system 10 times, then do step 4 | [5 empty] | Not test
N5(05)Windows Metadata check
1.Attach DUT into system 2.Power on system 3.Click "Start---Devices and Printers" after install driver 4.In devices category, check the device icon, NAme, shape, color 5.Select device icon and check devices information as above step 4 at the bottom 6.Right click the device icon, check link in pop menu 以及该选项所弹框的内容，能够适配DUT的测试 | [5 empty] | Not test
N5(06)PID/VID Check
Reference path: Device maNAger\DUT device\DUT Properties\Detail\Hardware Ids | [5 empty] | Not test
N5(07)System tray Icon check
Check the icon of the DUT in system tray at right bottom corner of the screen. | [5 empty] | Not test
N5(08)HW version check
1. Check HW version on sample body if it has label | [5 empty] | Not test
N5(09)FW update tool check
1. Install the driver 2. Check the FW version under OS 3.Repeat above steps 5 times 1. Install the driver 2. Check the FW version then update under OS 3.Repeat above steps 5 times 4.System and DUT can work normal | [5 empty] | Not test
N5(10)Cable Length Check N5(for wired product only)
Measure cable length | [5 empty] | Not test
N5(11)MS logo checkN5(only for win7 and win10 RS3)
1.Please refer to the attachment. | [5 empty] | Not test
History log :
User ID |  |  | Date
Defect list :
Defect list | Title |  |  | Severity | Priority | Creator | Status

## 2-Mouse Basic function t...
Basic:
Case type : | SW | Case ID: | MSA001_02
Case name : | Mouse Basic function test 01 | Category folder : | Mouse test case
Version : | V0.7 | Execution type : | Single
Keywords : | input | Status : | Active
Auto type :
Workloading : | 367(Min) | OS : | Win 11
Priority : | High | Phase : | CV,DVT
Creator : | yangbk2 | Owner : | yangbk2
Objective : | to verification the function of mouse | Release notes : | 分行
Type matrix : | Mouse Basic function test 01 | Case tools :
NA | Not support | Block | On going | Not start | Pass | Fail | Total
0 | 0 | 0 | 0 | 42 | 0 | 0 | 42
Comments :
Test case item |  |  |  | Expected result |  | Mouse Basic function test 01
Section : | Preparation (4) |  |  |  |  | Not test
Workloading : | (Min) | Leadingtime : | (Min) | Phase :
Preparation test units and download the latest preload image | [5 empty] | Not test
Section : | UserSwitchingTest (3) |  |  |  |  | Not test
Workloading : | (Min) | Leadingtime : | (Min) | Phase :
Please cover wired and wireless USB mouse and cover each USB port | [5 empty] | Not test
N5(01)Use admin account
1. Use admin account to enter OS. Install device's driver 2. Create another account with limited rights (limited account). |  |  |  | There's no any error during user switching and test. All functions work well under different user. There's no any error during user switching and test. " Device should function without error No Yellow bar Device MaNAger. Uninstallation driver should require administrator PW. |  | Not test
N5(02)Switch to another user
1. Switch to the another user 2. Run sniff test for the testing device |  |  |  | 同上 |  | Not test
N5(03)Logoff and logon
Logoff and logon with limited user. Check whether everything goes well .(This test might affect: Device MaNAger, Control Panel, software fucntion etc |  |  |  | 同上 |  | Not test
Section : | special sceNArio (60) |  |  |  |  | Not test
Workloading : | (Min) | Leadingtime : | (Min) | Phase :
Please cover wired and wireless USB mouse and cover each USB port | [5 empty] | Not test
N5 (01)Under Safe Mode
Safe mode: with mouse attached after the mouse suite installed, can boot to safe mode, without any BSoD or abnormal error. * Under safe mode BT devices do not work due to the BT driver is not loaded by OS. | [5 empty] | Not test
N5 (02)Under Dos/Shell/PE
DOS: with mouse attached after the mouse suite installed, system can enter DOS without any BSoD or abnormal error. | [5 empty] | Not test
N5 (03)Under Bios
BIOS: with mouse attached after the mouse suite installed, system can enter BIOS without any BSoD or abnormal error. | [5 empty] | Not test
Section : | 按键功能 (60) |  |  |  |  | Not test
Workloading : | (Min) | Leadingtime : | (Min) | Phase :
Please cover wired and wireless USB mouse and cover each USB port | [5 empty] | Not test
单键测试
1.使用mouse test 软件; 2.快速按键10s，是否有粘、漏键; 3.按住键慢慢松开，检查是否有粘、漏键 4.重复步骤1-3 5次 |  |  |  | 鼠标不应该出现粘键，漏键的情况，且没有其它异常 |  | Not test
多键测试
1.使用mouse test 软件 2.同时按下两个/多个键 3.检查是否有粘键或多发的现象 4.重复步骤1-3 5次 |  |  |  | 鼠标不应该出现粘键，漏键的情况，且没有其它异常 |  | Not test
离开桌面发码测试
1.使用mouse test 软件; 2.拿起鼠标离开桌面后; 3.按单个键/多键; 4.检查是否能正常发码; 5.重复步骤1-4 5次 |  |  |  | 鼠标可以正常发码，且没有其它异常 |  | Not test
长按单个按键测试
1.使用mouse test 软件; 2.长按单个按键5分钟，过程中按键是否有断开 3.长按单个按键5分钟，松手后按键是否能正常抬起 4.重复步骤1-3 5次 | [5 empty] | Not test
长按多个按键测试
1.使用mouse test 软件; 2.长按多键5分钟，过程中按键是否有断开 3.长按多键5分钟，松手后按键是否能正常抬起 4.重复步骤1-3 5次 | [5 empty] | Not test
按键移动测试
1.使用mouse test 软件; 2.按单个键或多键同时去移动鼠标1分钟 3.过程中按键是否有断开 4.重复步骤1-3 5次 | [5 empty] | Not test
敲击测试
1.使用mouse test 软件; 2.拿起鼠标离桌面5cm，连续敲击桌面10次 3.检查鼠标结构 |  |  |  | 1.外壳不能有开裂风险 2.结构件不能脱落情况 3.测试后检查鼠标基本功能 |  | Not test
Section : | 滚轮功能测试 (60) |  |  |  |  | Not test
Workloading : | (Min) | Leadingtime : | (Min) | Phase :
Please cover wired and wireless USB mouse and cover each USB port | [5 empty] | Not test
滚动精度测试
1.使用mouse test 软件; 2.连续不间断的前后各滚一格。 3.检查是否会有漏滚现象 4.检查软件中左上角W项是否是1和0的变化 5.重复步骤1-4 5次 | [5 empty] | Not test
连续滚动测试
1.使用mouse test 软件; 2.连续向前或后一个方向快速滚动 3.检查是否有漏滚或反滚的现象 4.重复步骤1-3 5次 | [5 empty] | Not test
按键+正常滚动测试
1.使用mouse test 软件; 2.按单个键或多键同时去向前或后滚动滚轮。 3.检查过程中是否有漏滚或反滚，按键是否有断开 4.重复步骤1-3 5次 | [5 empty] | Not test
按键+快速滚动测试
1.使用mouse test 软件; 2.快速向前或后一个方向快速滚动时，去按按键 3.检查是否有粘键或漏键 4.重复步骤1-3 5次 | [5 empty] | Not test
光标移动+滚轮测试
1.使用mouse test 软件; | [5 empty] | Not test
2.快速向前或后一个方向快速滚动时，移动鼠标 |  |  |  | 滚轮不能出现漏滚或者反滚情况 |  | Not test
3.检查是否有粘键、漏键或光标移动卡顿 |  |  |  | 滚轮不能出现漏滚或者反滚情况 |  | Not test
4.重复步骤1-3 5次 | [5 empty] | Not test
Section : | 唤醒测试 (60) |  |  |  |  | Not test
Workloading : | (Min) | Leadingtime : | (Min) | Phase :
Please cover wired and wireless USB mouse and cover each USB port | [5 empty] | Not test
系统唤醒测试
系统进入睡眠后，移动鼠标或单击任意按键均可唤醒系统 系统若支持其他模式可以用鼠标唤醒则其他模式也需要测试 |  |  |  | 不能出现无法唤醒系统 |  | Not test
Section : | 桌面性能测试 (60) |  |  |  |  | Not test
Workloading : | (Min) | Leadingtime : | (Min) | Phase :
Please cover wired and wireless USB mouse and cover each USB port | [5 empty] | Not test
鼠标垫材质适应性
1.将待测设备与系统连接； 2.在不同的鼠标垫上滑动； 3.在黑白纸滑动鼠标； 4.在以上材质上静置鼠标1分钟 | [5 empty] | Not test
画圆测试
1.使用mouse test 软件; 2.顺时针或逆时针画圆 3.以每秒移动5cm的速度，在桌面画圆（具体材质按照项目spec定义来选） 4.每个材质测试5分钟 5.检查画圆不可出现打折、光头抖动、报告率在标准值&plusmn;10范围 6.重复步骤1-5 5次 7.木桌/玻璃书桌/书本/上使用与竞品对比 | [5 empty] | Not test
快速画圆测试
1.打开控制面板 2.点鼠标选项中把指针移动速度设置成最慢 3.打开mouse test 软件，使用鼠标快速画圆 4.不可出现不打折或无法画圆 5.重复步骤1-4 5次 | [5 empty] | Not test
1.打开控制面板 2.点鼠标选项中把指针移动速度设置成最快 3.打开mouse test 软件，使用鼠标快速画圆 4.不可出现不打折或无法画圆 5.重复步骤1-4 5次 | [5 empty] | Not test
抖动测试
1.使用mouse test 软件; 2.将鼠标用卡片或者其他物品垫高，使其距离桌面1cm，如图所示 3.静置1分钟，观察光标不可出现抖动的情况，（mouse test中 X Y轴的数据不能发生变化） 4.重复步骤1-3 5次 | [5 empty] | Not test
移动+按键测试
1.使用mouse test 软件; 2.以每秒5cm的速度移动鼠标，移动过程中间歇测试按键功能或长按一键或多键同时移动鼠标 3.不能有漏键，出现抖动、打折 4.重复步骤1-3 5次 |  |  |  | 鼠标不能有漏键，出现抖动、打折 |  | Not test
Section : | LED 测试 (60) |  |  |  |  | Not test
Workloading : | (Min) | Leadingtime : | (Min) | Phase :
本地RGB测试
1.设置鼠标灯效/颜色为纯色 2.将系统进入S3/S4/S5状态 3.检查每次进入系统后鼠标RGB是否能够保持住之前的选择 |  |  |  | 1.电脑进入S3/S4/S5时，鼠标LED灭掉 2.电脑启动时，LED不能胡乱闪烁 3.电脑启动完成后，LED应恢复已完成设定值 |  | Not test
1.参照鼠标本地RGB 规范，依次检查灯效 |  |  |  | 1.切换按键符合标准 2.灯光颜色/效果符合标准 3.灯光顺序符合标准 4.能够切换并保持灯效 5.各种灯效不能有闪烁情况，(例如呼吸模式时有高频闪烁的情况) |  | Not test
动态光效
1.准备一台支持动态光效的电脑 2.接上待测键鼠,此时系统会有弹窗显示有支持动态光效的设备接入 3.点击动态光效设置,默认应为开启状态 a)点击关闭---动态光效关闭，恢复本地RGB b)点击开启---本地RGB关闭，动态光效启动 c)各效果亮度--- 0<--->100之间可以看到正确的亮度变化 各效果速度--- 最小值-最大值 之间可以看到正确的速度变化，且无闪烁异常 d)切换效果---纯色/呼吸/彩虹/波形/滚轮/渐变 ---每个效果需要人工确认至少5分钟确保连贯,顺畅,无突然闪烁 e)颜色效果----分别在每个RGB显示效果下设置主要颜色--次要颜色(设置10中自带颜色，以及3种自定义颜色) 如下测试需要cover 需要电脑上所有接口 4.热插拔鼠标20次, 检查状态 5.不同接口之间来回插拔5次，检查状态 6.系统进入锁屏 10次,检查状态 7.系统进入睡眠 10次，检查状态 8.系统进入休眠 10次，检查状态 9.重启系统10次，检查状态 10.开关机10次，检查状态 |  |  |  | 1.动态光效可以开启，关闭 2.亮度调可以控制LED亮度，速率调整控制LED行为速度 3.RGB效果显示符合选项,切换时顺畅连贯，无闪烁。 4.颜色效果可以任意设置并且符合设置目标颜色 5.电脑进入S3/S4/S5/状态时，动态灯效应关闭 6.电脑从S3/S4/S5/restart恢复进入系统后，动态光效应恢复 |  | Not test
动态光效全局设置
1.准备一台支持动态光效的电脑 2.接上待测键鼠 3.打开动态光效设置 4.开启匹配我的Windows主题颜色,设置至少3中不同的主题 5.检查光效颜色是否同步 6.做S3/S4/S5/restart 动作各3次，检查是否能保持灯效(需要cover 所有接口) 7.进行热拔插，检查是否能保持灯效(需要cover 所有接口) |  |  |  | 1.能匹配系统灯效 2.在电脑进入各种状态后能保持住灯效 |  | Not test
多设备同步测试(全局模式)
接至少两台支持动态光效的设备(不同种类) 1.若电脑显示两台设备等效不一致，点击重置 2.依次测试全局模式---灯效开关/亮度/效果/颜色/主题 3.进行S3/S4/S5/Restart/Hot plug 动作 各5次 4.检查多设备灯效同步情况 |  |  |  | 1.多设备灯效应同步显示 2.多设备插拔或者恢复链接后应能保持已设置好的效果 |  | Not test
微软<->本地RGB逻辑切换
1.鼠标切换到到本地RGB中的一种光效，系统打开动态光效 2.使用本地RGB控制按键,如本地RGB切换，开关,亮度大小，以及其他控制LED，(参考SPEC,切换本地RGB) 3.使用高优先级LED指示灯,以及SPEC 要求的最高优先级LED 4.点击RGB打开/关闭 至少开关20次，检查灯效是否能够每次都切换成功 |  |  |  | 1.本地RGB 与微软RGB优先级区别， 2.本地RGB 与微软RGB 不能有冲突 3.开启关闭每次都要成功 4，关闭时应该恢复至选择的本地RGB，而不是默认初始RGB |  | Not test
测试目的:在锁屏界面 1.启动动态光效 2.设置密码并将电脑进入锁屏状态 3.检查鼠标动态灯效 4.此时打开本地RGB光效 5.通过鼠标唤醒电脑 6.检查RGB光效 |  |  |  | 1.系统进入锁屏状态后键盘RGB应该同步系统光效为OFF状态 2.唤醒电脑后, 可以正常关闭本地的RGB |  | Not test
History log :
User ID |  |  | Date
Defect list :
Defect list | Title |  |  | Severity | Priority | Creator | Status

## 3-Mouse Scenario test 02
Basic:
Case type : | SW | Case ID: | MSA001_03
Case name : | Mouse Scenario test 02 | Category folder : | Mouse test case
Version : | V0.4 | Execution type : | Single
Keywords : | input | Status : | Active
Auto type :
Workloading : | 434(Min) | OS :
Priority : |  | Phase :
Creator : | yangbk2 | Owner : | yangbk2
Objective : | To verification mouse compatibility | Release notes : | 分行
Type matrix : | Mouse Scenario test 02 | Case tools :
NA | Not support | Block | On going | Not start | Pass | Fail | Total
0 | 0 | 0 | 0 | 38 | 0 | 0 | 38
Comments :
Test case item |  |  |  | Expected result |  | Mouse Scenario test 02
Section : | Preparation (4) |  |  |  |  | Not test
Workloading : | (Min) | Leadingtime : | (Min) | Phase :
Preparation test units and download the latest preload image/driver/BIOS etc.. |  |  |  | Expected Result1 |  | Not test
Section : | DPI功能测试 (60) |  |  |  |  | Not test
Workloading : | (Min) | Leadingtime : | (Min) | Phase :
Please cover wired and wireless USB mouse and cover each USB port | [5 empty] | Not test
默认DPI
1.鼠标初次开机并连接电脑（驱动中恢复出厂设置） 2.在设置里检查鼠标的默认DPI |  |  |  | 根据Spec定义 |  | Not test
切换记忆
1.检查鼠标每档DPI切换成功后，移动是否有发生变化 2.检查鼠标每档DPI切换成功时,所提示的LED灯是否正常（如果鼠标有LED灯的话） 3.重复步骤1-2 5次 |  |  |  | 切换DPI后，鼠标移动速度会发生变化 LED会随着DPI切换发生变化 |  | Not test
上电记忆
1.测试切换每一档DPI成功后 2.鼠标重新上电或拔插Dongle 3.检查是否有保存记忆功能 4.重复步骤1-3 5次 |  |  |  | 重新上电或者接入dongle后，应保持关机或者拔掉donlge时的DPI值 |  | Not test
PM记忆
1.测试切换每一档DPI成功后 2.使PC进入S3/S4/S5/restart唤醒后 3.检查是否有保存记忆功能 4.重复步骤1-3 5次 |  |  |  | PC唤醒后，鼠标应保持 S0时的DPI值 |  | Not test
Section : | 上下电测试 (60) |  |  |  |  | Not test
Workloading : | (Min) | Leadingtime : | (Min) | Phase :
Please cover wired and wireless USB mouse and cover each USB port | [5 empty] | Not test
快速上下电
1.快速上电：使鼠标在1分钟之内上下电（开关鼠标） 2.慢速上电：使鼠标在5分钟之内上下电 3.检查鼠标是否可以正常使用 4.重复步骤1-3 5次 |  |  |  | 鼠标使用正常，不能出现不能使用或者无法开机的情况 |  | Not test
误操作上电
1.同时按住左右键上电 2.按住中键上电 3.按住两侧键(或其它组合键）上电 4.检查鼠标上电后能正常工作，比如粘键等异常问题。 ‘ 5.重复步骤1-4 10次 |  |  |  | 鼠标按键不能出现粘键，或者不能使用等异常情况 |  | Not test
Section : | 电量显示检查 (60) |  |  |  |  | Not test
Workloading : | (Min) | Leadingtime : | (Min) | Phase :
Please cover wired and wireless USB mouse and cover each USB port | [5 empty] | Not test
OS中鼠标电量检查
1.蓝牙1 2.蓝牙2 3.2.4G |  |  |  | 无异常 |  | Not test
Section : | 优先级测试 (60) |  |  |  |  | Not test
Workloading : | (Min) | Leadingtime : | (Min) | Phase :
Please cover wired and wireless USB mouse and cover each USB port | [5 empty] | Not test
高优先级转到低优先级
1.鼠标用3中模式与一台电脑连接上 2.此时有线的优先级最高，有线模式正常工作 3.拔掉USB线，鼠标自动切换到2.4 G 模式，且工作正常 4.拔掉2.4G dongle，鼠标自动切换到蓝牙模式 5.蓝牙模式下工作正常 6.重复5次 |  |  |  | 1.三个模式可以自由切换 2.鼠标切换时回连时间不能太长 3.回连时鼠标无卡顿 4.回连后鼠标可以正常工作 |  | Not test
低优先级转高优先级
1.鼠标与电脑蓝牙配对，此时蓝牙模式下鼠标正常工作 2.将2.4G dongle 接入电脑，鼠标自动切换到2.4G 模式下，正常工作 3.将USB线接入电脑，鼠标有线模式下，鼠标正常工作 4.重复5次 |  |  |  | 1.三个模式可以自由切换 2.鼠标切换时回连时间不能太长 3.回连时鼠标无卡顿 4.回连后鼠标可以正常工作 |  | Not test
Section : | 模式切换测试 (60) |  |  |  |  | Not test
Workloading : | (Min) | Leadingtime : | (Min) | Phase :
Please cover wired and wireless USB mouse and cover each USB port | [5 empty] | Not test
有线切换到2.4G
1.将2.4G dongle接入NB，鼠标调到2.4G模式 2.观察鼠标是否可以正常使用 3.将USB线接入NB 4.观察鼠标是否有卡顿，无功能的情况 5.拔掉USB线，观察鼠标是否可以正常使用 6.重复5次 |  |  |  | 1.两种模式可自由切换 2.切换过程中，没有出现鼠标卡住不能用的情况 3.切换完成后鼠标无卡顿现象 |  | Not test
(02)有线切换到BT
1.鼠标与NB，蓝牙配对成功 2.观察鼠标是否可以正常使用 3.将USB线接入NB 4.观察鼠标是否有卡顿，无功能的情况 5.拔掉USB线，观察鼠标是否可以正常使用 6.记录鼠标的回连时间是否符合要求，鼠标是否可以正常使用 7.重复5次 |  |  |  | 1.两种模式可自由切换 2.切换过程中，没有出现鼠标卡住不能用的情况 3.切换完成后鼠标无卡顿现象 4.鼠标BT模式回连时间符合spec |  | Not test
（03）2.4G切换BT
1.鼠标与NB，蓝牙配对成功 2.观察鼠标是否可以正常使用 3.将2.4G dongle接入PC， 4.观察鼠标是否正常使用 5.将鼠标模式调至2.4G 6.观察蓝牙是否断开，鼠标是否可以正常使用 7.将鼠标模式调至BT模式 8.记录鼠标的回连时间是否符合要求，鼠标是否可以正常使用 9.重复5次 |  |  |  | 1.两种模式可自由切换 2.切换过程中，没有出现鼠标卡住不能用的情况 3.切换完成后鼠标无卡顿现象 4.鼠标BT模式回连时间符合spec |  | Not test
（04）雙BT和2.4G模式自由切换(3台电脑)
1.鼠标蓝牙1与电脑A配对 2.鼠标的2.4G dongle接入电脑B 3.鼠标的BT2接入电脑C，此时鼠标在电脑C正常工作 4.切换到2.4G，鼠标正常切换到电脑B正常工作 5.切换到蓝牙1，鼠标在电脑A，蓝牙模式正常工作 6.重复5次 |  |  |  | 1.三个模式可以自由切换 2.鼠标切换时回连时间不能太长 3.回连时鼠标无卡顿 4.回连后鼠标可以正常工作 |  | Not test
（04）雙BT和2.4G模式自由切换(1台电脑)
1.鼠标与电脑蓝牙配对，此时蓝牙模式下鼠标正常工作 2.将2.4G dongle 接入电脑，鼠标自动切换到2.4G 模式下，正常工作 3.将BT2配对电脑，鼠标切换到BT2，鼠标正常工作 4.重复5次 |  |  |  | 1.三个模式可以自由切换 2.鼠标切换时回连时间不能太长 3.回连时鼠标无卡顿 5.回连后鼠标可以正常工作 |  | Not test
Section : | 特殊按键功能检查 (60) |  |  |  |  | Not test
Workloading : | (Min) | Leadingtime : | (Min) | Phase :
Please cover wired and wireless USB mouse and cover each USB port | [5 empty] | Not test
（01）DPI button
检查按键功能是否正常 |  |  |  | 符合SPEC |  | Not test
（02）Steal mode（截屏）
检查按键功能是否正常 |  |  |  | 符合SPEC |  | Not test
（03）BT/2.4G
检查按键功能是否正常 |  |  |  | 符合SPEC |  | Not test
（04）侧键
检查按键功能是否正常 |  |  |  | 符合SPEC |  | Not test
（05）滚轮
检查按键功能是否正常 |  |  |  | 符合SPEC |  | Not test
Section : | 充电场景测试 (60) |  |  |  |  | Not test
Workloading : | (Min) | Leadingtime : | (Min) | Phase :
Please cover wired and wireless USB mouse and cover each USB port | [5 empty] | Not test
（1）正常配对测试
准备一个没电的设备 1.将DUT接入电源适配器 2.DUT和PC链接成功 3.使用5分钟 |  |  |  | 鼠标正常工作, 各按键无异常， 检查LED符合当前设置， 无卡顿断链 指针跟手 |  | Not test
（1）配对超时测试
1.将DUT接入电源适配器 2.DUT与PC1链接成功 3,DUT再次进入配对模式(dongle为移除--等待鼠标进入休眠后再次接入dongle) 4.等待配对超时后，检查DUT是否会回连到上一个host |  |  |  | 1.鼠标正常工作 2.各按键无异常 检查LED符合当前设置 无卡顿锻炼 指针跟手 |  | Not test
（2）S3回连测试
1.将DUT接入电源适配器 2.DUT和PC蓝牙配对成功(dongle 为直接插入) 3.PC进入S3模式后唤醒 4.检查DUT是否正常回连到Host 5.将原配充电线一端接入DUT一端接入PC 重复测试2-4 5次 |  |  |  | 鼠标正常工作,不超时无异常，LED符合当前设置，无卡顿锻炼，指针跟手 |  | Not test
（2）S4回连测试
1.将DUT接入电源适配器 2.DUT和PC蓝牙配对成功(dongle 为直接接入) 3.PC进入S4模式后唤醒 4.检查DUT是否正常回连到Host 5.将原配充电线一端接入DUT一端接入PC 重复测试2-4 5次 |  |  |  | 鼠标正常工作,不超时无异常 |  | Not test
（2）S5回连测试
1.将DUT接入电源适配器 2.DUT和PC蓝牙配对成功(dongle为直接插入) 3.PC进入S5模式后唤醒 4.检查DUT是否正常回连到Host 5.将原配充电线一端接入DUT一端接入PC 重复测试2-4 5次 |  |  |  | 鼠标正常工作,不超时无异常 |  | Not test
（2）重启回连测试
1.将DUT接入电源适配器 2.DUT和PC蓝牙配对成功(dongle 为直连) 3.PC重启 4.检查DUT是否正常回连到Host 5.将原配充电线一端接入DUT一端接入PC 重复测试2-4 5次 |  |  |  | 鼠标正常工作,不超时无异常 |  | Not test
（2）锁屏回连测试
1.将DUT接入电源适配器 2.DUT和PC蓝牙配对成功(dongle 为直连) 3.PC锁屏后进入桌面 4.检查DUT是否正常回连到Host 5.将原配充电线一端接入DUT一端接入PC 重复测试2-4 5次 |  |  |  | 鼠标正常工作,不超时无异常 |  | Not test
（2）关盖子回连测试
1.将DUT接入电源适配器并链接电脑 3.PC关闭盖子后打开 4.检查DUT是否正常回连到Host 5.将原配充电线一端接入DUT一端接入PC 重复测试2-4 5次 (关闭盖子分别设置为无动作/S3/S4/S5) |  |  |  | 鼠标正常工作,不超时无异常 |  | Not test
Section : | 敲击测试 (10) |  |  |  |  | Not test
Workloading : | (Min) | Leadingtime : | (Min) | Phase :
Please cover wired and wireless USB mouse and cover each USB port | [5 empty] | Not test
（01）外观检查
检查外观是否存在瑕疵 |  |  |  | 无划痕损伤等不良情况 |  | Not test
（02）敲击测试
敲击鼠标外观结构 |  |  |  | 鼠标不能出现结构脱落 变型 |  | Not test
History log :
User ID |  |  | Date
Defect list :
Defect list | Title |  |  | Severity | Priority | Creator | Status

## 4-Mouse Basic function t...
Basic:
Case type : | SW | Case ID: | MSA001_04
Case name : | Mouse Basic function test 02 | Category folder : | Mouse test case
Version : | V0.4 | Execution type : | Single
Keywords : | input | Status : | Active
Auto type :
Workloading : | 399(Min) | OS :
Priority : |  | Phase :
Creator : | yangbk2 | Owner : | yangbk2
Objective : | to verification mouse function with out SW | Release notes : | 分行
Type matrix : | Mouse Basic function test 02 | Case tools :
NA | Not support | Block | On going | Not start | Pass | Fail | Total
0 | 0 | 0 | 0 | 41 | 0 | 0 | 41
Comments :
Test case item |  |  |  | Expected result |  | Mouse Basic function test 02
Section : | Preparation (4) |  |  |  |  | Not test
Workloading : | (Min) | Leadingtime : | (Min) | Phase :
Preparation test units and download the latest preload image/driver/BIOS etc.. |  |  |  | Expected Result1 |  | Not test
Section : | 無軟件功能測試 (30) |  |  |  |  | Not test
Workloading : | (Min) | Leadingtime : | (Min) | Phase :
Please cover wired and wireless USB mouse and cover each USB port | [5 empty] | Not test
单键测试
1.使用mouse test 软件; 2.快速按键10s，是否有粘、漏键; 3.按住键慢慢松开，检查是否有粘、漏键 4.重复步骤1-3 5次 | [5 empty] | Not test
双键测试
1.使用mouse test 软件; 2.同时按下两个或多个键 3.检查是否有粘键或多发的现象 4.重复步骤1-3 5次 | [5 empty] | Not test
离开桌面发码测试
1.使用mouse test 软件; 2.拿起鼠标离开桌面后; 3.按单个键或多键; 4.检查是否能正常发码; 5.重复步骤1-4 5次 | [5 empty] | Not test
长按单键测试
1.使用mouse test 软件; 2.长按单个按键5分钟，过程中按键是否有断开 3.长按单个按键5分钟，松手后按键是否能正常抬起 4.重复步骤1-3 5次 | [5 empty] | Not test
长按多键测试
1.使用mouse test 软件; 2.长按多键5分钟，过程中按键是否有断开 3.长按多键5分钟，松手后按键是否能正常抬起 4.重复步骤1-3 5次 | [5 empty] | Not test
按键移动测试
1.使用mouse test 软件; 2.按单个键或多键同时去移动鼠标1分钟 3.过程中按键是否有断开 4.重复步骤1-3 5次 | [5 empty] | Not test
敲击测试
1.使用mouse test 软件; 2.拿起鼠标离桌面5cm，连续敲击桌面10次 3.检查是否会有发码的现象 4.重复步骤1-3 6次 | [5 empty] | Not test
Section : | 滚轮功能测试 (60) |  |  |  |  | Not test
Workloading : | (Min) | Leadingtime : | (Min) | Phase :
Please cover wired and wireless USB mouse and cover each USB port | [5 empty] | Not test
滚动精度测试
1.使用mouse test 软件; 2.连续不间断的前后各滚一格。 3.检查是否会有漏滚现象 4.检查软件中左上角W项是否是1和0的变化 5.重复步骤1-4 5次 | [5 empty] | Not test
连续滚动测试
1.使用mouse test 软件; 2.连续向前或后一个方向快速滚动 3.检查是否有漏滚或反滚的现象 4.重复步骤1-3 5次 | [5 empty] | Not test
按键+滚动测试
1.使用mouse test 软件; 2.按单个键或多键同时去向前或后滚动滚轮。 3.检查过程中是否有漏滚或反滚，按键是否有断开 4.重复步骤1-3 5次 | [5 empty] | Not test
按键+快速滚动
1.使用mouse test 软件; 2.快速向前或后一个方向快速滚动时，去按按键 3.检查是否有粘键或漏键 4.重复步骤1-3 5次 |  |  |  | 1.鼠标滚动方向正常 2.按键不能出现断开 |  | Not test
光标移动+滚轮测试
1.使用mouse test 软件; 2.快速向前或后一个方向快速滚动时，移动鼠标 3.检查是否有粘键、漏键或光标移动卡顿 4.重复步骤1-3 5次 |  |  |  | 滚轮不能出现漏滚或者反滚情况 |  | Not test
Section : | 重连测试 (60) |  |  |  |  | Not test
Workloading : | (Min) | Leadingtime : | (Min) | Phase :
S5
1.将系统进入S5状态， 确认系统已经关闭 2.等待3分钟 3.开机，检查键鼠状态 4.重复1-3 5次 |  |  |  | 关机/开机过程以及完成后，均需要确认键盘LED/RGB状态 |  | Not test
Restart
1.通过开始界面重启电脑 2.电脑重启过程中，以及重启完成后， 均需要检查设备LED / RGB状态 重复5次 |  |  |  | 1./LEDRGB不能异常闪烁 |  | Not test
S4
1.将系统进入S4状态，确认系统已经休眠 2.等待3分钟 3.开机，检查鼠标状态 4.重复1-3 5次 |  |  |  | 过程中，以及完成动作后均需要确认RGB/LED 状态 |  | Not test
S3
1.将系统进入S3状态，确认系统已经睡眠 2.等待3分钟 3.通过鼠标唤醒电脑，检查鼠标状态 4.重复1-3 5次 |  |  |  | 1.睡眠过程中检查LED./RGB 关闭 2.RGB不能异常闪烁 |  | Not test
Section : | 长时间静置测试 (5) |  |  |  |  | Not test
Workloading : | (Min) | Leadingtime : | (Min) | Phase :
S4
1.接上鼠标，检查工作状态 2.让系统进入S4模式 3.确保系统进入S4 模式， 静置2H 4.唤醒系统，检查鼠标工作状态 |  |  |  | 1.电脑不能有卡顿 2.鼠标RGB..LED正常 |  | Not test
S3
1.接上鼠标，检查工作状态 2.让系统进入S3模式 3.确保系统进入S3模式，静置2H 4.唤醒系统，检查鼠标工作状态 | [5 empty] | Not test
S5
1.接上鼠标，检查工作状态 2.让系统进入S5， 3.确保系统进入S5，静置6H 4.开机，检查鼠标工作状态 | [5 empty] | Not test
Section : | 3.唤醒测试 (60) |  |  |  |  | Not test
Workloading : | (Min) | Leadingtime : | (Min) | Phase :
Please cover wired and wireless USB mouse and cover each USB port | [5 empty] | Not test
系统唤醒测试
场景1:按键唤醒: 1.电脑进入睡眠模式 2.鼠标应全按键均可唤醒电脑 场景2：移动唤醒 移动唤醒: 1.系统进入睡眠状态 2.通过移动鼠标唤醒电脑 |  |  |  | 1.鼠标可唤醒电脑 2.不可唤醒时需要记录问题，及时与PA联系确认当前产品及电脑SPEC，由PA判定是否符合规格 通常情况,每个案子都需要和PA核对: 1.有线模式+台式 ： 按键唤醒， 移动唤不醒 有线模式+笔记本：按键唤醒，移动可唤醒 2.无线模式：均需要移动唤醒和按键唤醒。 |  | Not test
Section : | 4.桌面性能测试 (60) |  |  |  |  | Not test
Workloading : | (Min) | Leadingtime : | (Min) | Phase :
Please cover wired and wireless USB mouse and cover each USB port | [5 empty] | Not test
鼠标垫材质适应性
1.将待测设备与系统连接； 2.在不同的鼠标垫上滑动； 3.在黑白纸滑动鼠标； 4.在以上材质上静置鼠标1分钟 |  |  |  | 待测设备箭头滑动顺畅，无跳动、不动现象； 静置时鼠标箭头无移动。 |  | Not test
报告率测试
1.运行软件(Mouse test.exe) 2.将Dongle连接到系统的USB A/C端口 3.在进行画圆圈，确保鼠标不会出现响应延迟 4.检查鼠标报告率在标准值&plusmn;10范围 5.依次切换PC的USB A/C端口，确保每个接口都测试到 6.关开鼠标后重复步骤1-5 5次 7.将2个鼠标接入系统，重复步骤1-6，检查报告率的变化和对鼠标功能的影响 | [5 empty] | Not test
画圆测试
1.使用mouse test 软件; 2.顺时针或逆时针画圆 3.以每秒移动5cm的速度，在桌面画圆（具体材质按照项目spec定义来选） 4.每个材质测试5分钟 5.检查画圆不可出现打折、光头抖动、报告率在标准值&plusmn;10范围 6.重复步骤1-5 5次 | [5 empty] | Not test
快速画圆测试
1.打开控制面板 2.点鼠标选项中把指针移动速度设置成最慢 3.打开mouse test 软件，使用鼠标快速画圆 4.不可出现不打折或无法画圆 5.重复步骤1-4 5次 |  |  |  | 不可出现不打折或无法画圆 |  | Not test
1.打开控制面板 2.点鼠标选项中把指针移动速度设置成最快 3.打开mouse test 软件，使用鼠标快速画圆 4.不可出现不打折或无法画圆 |  |  |  | 不可出现不打折或无法画圆 |  | Not test
5.重复步骤1-4 5次 |  |  |  | 不可出现不打折或无法画圆 |  | Not test
抖动测试
1.使用mouse test 软件; 2.将鼠标用卡片或者其他物品垫高，使其距离桌面1cm，如图所示 3.静置1分钟，观察光标不可出现抖动的情况，（mouse test中 X Y轴的数据不能发生变化） 4.重复步骤1-3 5次 |  |  |  | 观察光标不可出现抖动的情况 |  | Not test
移动+按键测试
1.使用mouse test 软件; 2.以每秒5cm的速度移动鼠标，移动过程中间歇测试按键功能或长按一键或多键同时移动鼠标 3.不能有漏键，出现抖动、打折 4.重复步骤1-3 5次 |  |  |  | 鼠标不能有漏键，出现抖动、打折 |  | Not test
Section : | 5.DPI功能测试 (60) |  |  |  |  | Not test
Workloading : | (Min) | Leadingtime : | (Min) | Phase :
Please cover wired and wireless USB mouse and cover each USB port | [5 empty] | Not test
默认DPI
1.鼠标初次开机并连接电脑（驱动中恢复出厂设置） 2.在设置里检查鼠标的默认DPI |  |  |  | follow spec |  | Not test
切换记忆
1.检查鼠标每档DPI切换成功后，移动是否有发生变化 2.检查鼠标每档DPI切换成功时,所提示的LED灯是否正常（如果鼠标有LED灯的话） 3.重复步骤1-2 5次 |  |  |  | 切换DPI后，鼠标移动速度会发生变化 LED会随着DPI切换发生变化 |  | Not test
上电记忆
1.测试切换每一档DPI成功后 2.鼠标重新上电或拔插Dongle 3.检查是否有保存记忆功能 4.重复步骤1-3 5次 |  |  |  | 重新上电或者接入dongle后，应保持关机或者拔掉donlge时的DPI值 |  | Not test
PM记忆
1.测试切换每一档DPI成功后 2.使PC进入S3/S4/S5/restart唤醒后 3.检查是否有保存记忆功能 4.重复步骤1-3 5次 |  |  |  | PC唤醒后，鼠标应保持 S0时的DPI值 |  | Not test
Section : | 6.上下电测试 (60) |  |  |  |  | Not test
Workloading : | (Min) | Leadingtime : | (Min) | Phase :
Please cover wired and wireless USB mouse and cover each USB port | [5 empty] | Not test
快速上下电
1.快速上电：使鼠标在1分钟之内上下电（开关鼠标） 2.慢速上电：使鼠标在5分钟之内上下电 3.检查鼠标是否可以正常使用 4.重复步骤1-3 5次 |  |  |  | 鼠标使用正常，不能出现不能使用或者无法开机的情况 |  | Not test
误操作上电
1.同时按住左右键上电 2.按住中键上电 3.按住两侧键(或其它组合键）上电 4.检查鼠标上电后能正常工作，比如粘键等异常问题。 5.重复步骤1-4 10次 |  |  |  | 鼠标按键不能出现粘键，或者不能使用等异常情况 |  | Not test
History log :
User ID |  |  | Date
Defect list :
Defect list | Title |  |  | Severity | Priority | Creator | Status

## 5-Plug test(matrix)
Basic:
Case type : | SW | Case ID: | MSA001_05
Case name : | Plug test(matrix) | Category folder : | Mouse test case
Version : | V0.2 | Execution type : | Single
Keywords : | input | Status : | Active
Auto type :
Workloading : | 90(Min) | OS :
Priority : |  | Phase :
Creator : | yangbk2 | Owner : | yangbk2
Objective : | to verification compatibility | Release notes : | TITLE CHANGED
Type matrix : | Plug test(matrix) | Case tools :
NA | Not support | Block | On going | Not start | Pass | Fail | Total
0 | 0 | 0 | 0 | 7 | 0 | 0 | 7
Comments :
Test case item |  |  |  | Expected result |  | Plug test(matrix)
Section : | Plug test matrix (90) |  |  |  |  | Not test
Workloading : | (Min) | Leadingtime : | (Min) | Phase :
Please cover wired and wireless USB mouse and cover each USB port | [5 empty] | Not test
Hot plug (10 times)
Enter OS Plug dock in Unplug dock Wait for more than 10s Plug dock in |  |  |  | 1.No yellow mark in device management 2.The monitor of DUT display normal without error message and garbage. 3.All devices of DUT can be recognized and work normally 4.Make sure DUT power button is normal and the Power Button LED is meet the spec. 5.Charging status. 1.设备管理中没有黄色标记 2.DUT监视器显示正常，无错误信息和垃圾。 3.DUT的所有设备都能被识别并正常工作 4.确保DUT电源按钮正常，电源按钮LED灯符合规格。 5.充电状态。 |  | Not test
OS in S3 - plug (10 times)
Enter OS Plug dock in Unplug dock Wait for more than 10s Make system enter S3 totally Plug dock in Resume system | [5 empty] | Not test
OS in S3 - unplug (10 times)
Enter OS Plug dock in Make system enter S3 totally Unplug dock Wait for more than 10s Resume system Plug dock in | [5 empty] | Not test
OS in S4 - plug (10 times)
Enter OS Plug dock in Unplug dock Wait for more than 10s Make system enter S4 totally Plug dock in Resume system | [5 empty] | Not test
OS in S4 - unplug (10 times)
Enter OS Plug dock in Make system enter S4 totally Unplug dock Wait for more than 10s Resume system Plug dock in | [5 empty] | Not test
Cold attach dock (10 times)
Make sure system is turn off Plug dock in Turn on system | [5 empty] | Not test
History log :
User ID |  |  | Date
Defect list :
Defect list | Title |  |  | Severity | Priority | Creator | Status

## 6-Mouse Basic function t...
Basic:
Case type : | SW | Case ID: | MSA001_06
Case name : | Mouse Basic function test 03 | Category folder : | Mouse test case
Version : | V0.3 | Execution type : | Single
Keywords : | input | Status : | Active
Auto type :
Workloading : | 1054(Min) | OS :
Priority : |  | Phase :
Creator : | yangbk2 | Owner : | yangbk2
Objective : | to verification function | Release notes : | update attachment
Type matrix : | Mouse Basic function test 03 | Case tools :
NA | Not support | Block | On going | Not start | Pass | Fail | Total
0 | 0 | 0 | 0 | 114 | 0 | 0 | 114
Comments :
Test case item |  |  |  | Expected result |  | Mouse Basic function test 03
Section : | Preparation (4) |  |  |  |  | Not test
Workloading : | (Min) | Leadingtime : | (Min) | Phase :
Preparation test units and download the latest preload image/driver/BIOS etc.. 请下载附件 并把测试数据记录于附件中上传至系统 |  |  |  | Expected Result1 |  | Not test
Section : | 1.LED灯测试 (90) |  |  |  |  | Not test
Workloading : | (Min) | Leadingtime : | (Min) | Phase :
Please cover wired and wireless USB mouse and cover each USB port 1.依规格测试鼠标各种指示灯：DPI切换、电量低压、配对成功&超时、充电状态、满电状态、上下电指示灯等 2.检查以上各种指示灯是否显示正常 3.重复步骤1-2 5次 | [5 empty] | Not test
Power On
Power On |  |  |  | Follow Spec |  | Not test
Battery Low <=10%
Battery Low <=10% |  |  |  | Follow Spec |  | Not test
Battery Charging
Battery Charging |  |  |  | Follow Spec |  | Not test
Not pair
Not pair |  |  |  | Follow Spec |  | Not test
Pair with dongle/BT
Pair with dongle/BT |  |  |  | Follow Spec |  | Not test
When pair button pressed
When pair button pressed |  |  |  | Follow Spec |  | Not test
Short press pairing key when DUT has paired
Short press pairing key when DUT has paired |  |  |  | Follow Spec |  | Not test
Press DPI key
Press DPI key |  |  |  | Follow Spec |  | Not test
Section : | 2.充电测试 (60) |  |  |  |  | Not test
Workloading : | (Min) | Leadingtime : | (Min) | Phase :
充电电压: follow spec ，电流: follow Spec 上传充电曲线图 | [5 empty] | Not test
样品1(有线充电)
0%~100% 3个样品数据 |  |  |  | 1.充电时间符合SPEC |  | Not test
样品1(无线充电)
0%~100% 3个样品数据 |  |  |  | 1.充电时间符合SPEC |  | Not test
样品1(有线充电)
充电15分钟 3个样品数据 |  |  |  | 充电15分钟，使用时间符合Spec |  | Not test
样品1(无线充电)
充电15分钟 3个样品数据 |  |  |  | 充电15分钟，使用时间符合Spec |  | Not test
Section : | 放电测试 (60) |  |  |  |  | Not test
Workloading : | (Min) | Leadingtime : | (Min) | Phase :
样品1
100%-0% 3个样品数据 |  |  |  | 放电时间符合Spec |  | Not test
低电量放电测试 3个样品数据 |  |  |  | 放电时间符合Spec |  | Not test
Section : | 功耗测试 (60) |  |  |  |  | Not test
Workloading : | (Min) | Leadingtime : | (Min) | Phase :
不同工作状态下的功耗
每个案子不同方法,ODM提出测试方案研发审核后开始测试并提供结果 1.持续给鼠标充电，待鼠标达到满电后，观察耗电情况 2.待鼠标满电后，接入电流计，观察耗电情况 3.持续使用鼠标，待电池达到cut off状态 4.鼠标cut off 后直接上电 |  |  |  | 符合RFQ SPEC |  | Not test
Section : | 过充/过放/过压测试 (60) |  |  |  |  | Not test
Workloading : | (Min) | Leadingtime : | (Min) | Phase :
过充测试： 1. DUT are fully charged 2.DUT connected with twice the rated voltage and current, and the adapter is charged continuously for 48 hours 3.After the test, DUT charge and discharge were normal 过放测试： 1.Discharge DUT until it shuts down automatically, power on DUT several times until it can't power on. 2.After 4 weeks of placement, check if DUT can charge and work normal. 3.Test total 5 sample 过压测试： 1. DUT充满电 2.DUT连接两倍额定电压和电流，适配器连续充电48小时（有过压保护，无法充电） 3.测试后DUT充放电正常 | [5 empty] | Not test
过充测试样品1
3个样品数据 | [5 empty] | Not test
过放测试样品1
3个样品数据 | [5 empty] | Not test
过压测试样品1
3个样品数据 | [5 empty] | Not test
Section : | 三方电源兼容性 (60) |  |  |  |  | Not test
Workloading : | (Min) | Leadingtime : | (Min) | Phase :
电源兼容性
1.使用Adapter和第三方充电器给鼠标充电，鼠标充电正常，不能出现短路，或者无法充满等情况 2.检查鼠标锂电池是否有做电池保护，不能出现鼠标元器件或电阻等配件烧坏 测试5个样品 1.联想45W/65W/100W/135W/140W电源 2.华为电源 3.小米电源 4.小米QI无线充 5.华为QI无线充 6.联想QI无线充 | [5 empty] | Not test
Section : | 2.4G干扰测试 (60) |  |  |  |  | Not test
Workloading : | (Min) | Leadingtime : | (Min) | Phase :
步骤： 0.把Dock和Hub的FW和Driver更新到最新版本 1. 把金属U盘和鼠标dongle接入相邻的USB接口中(每一个USB接口都需要测试） 2. Keep mouse away from dongle 20/50/100/150 cm and front 0/45/-45 degree 3. Use Areson Mouse test program to test if mouse move any lag. 标准： 1.U disk needs to transmit data during test 2.Using mosue tset to test drawing circle can't be stuck crosscheck: 每个场景均需要对比竞品表现 | [5 empty] | Not test
PC+金属U盘
left 45&deg; | [5 empty] | Not test
vertical 0&deg; | [5 empty] | Not test
right 45&deg; | [5 empty] | Not test
PC+显示器+金属U盘
left 45&deg; | [5 empty] | Not test
vertical 0&deg; | [5 empty] | Not test
right 45&deg; | [5 empty] | Not test
PC+USB C GEN2 Dock+金属U盘
left 45&deg; | [5 empty] | Not test
vertical 0&deg; | [5 empty] | Not test
right 45&deg; | [5 empty] | Not test
PC+TBT GEN2 Dock+金属U盘
left 45&deg; | [5 empty] | Not test
vertical 0&deg; | [5 empty] | Not test
right 45&deg; | [5 empty] | Not test
PC+ USB-C Hub +金属U盘
left 45&deg; | [5 empty] | Not test
vertical 0&deg; | [5 empty] | Not test
right 45&deg; | [5 empty] | Not test
PC+绿联 Hub +金属U盘
left 45&deg; | [5 empty] | Not test
vertical 0&deg; | [5 empty] | Not test
right 45&deg; | [5 empty] | Not test
Section : | 切换设备和BT回连时间测试 (60) |  |  |  |  | Not test
Workloading : | (Min) | Leadingtime : | (Min) | Phase :
测试5个样品并记录时间并且回连符合Spec | [5 empty] | Not test
切换设备时间
PC1(Dongle)切换至PC2(BT) | [5 empty] | Not test
PC2(BT)切换至PC3(BT) | [5 empty] | Not test
PC3(BT)切换至PC1(Dongle） | [5 empty] | Not test
BT模式自动回连时间
S3 | [5 empty] | Not test
S4 | [5 empty] | Not test
S5 | [5 empty] | Not test
Section : | Cable检查 (60) |  |  |  |  | Not test
Workloading : | (Min) | Leadingtime : | (Min) | Phase :
Cable 实物检查
检查自带cable的各项参数是否符合Spec 依case: 长度、线径、数据传输、电源传输等是否符合Spec | [5 empty] | Not test
Section : | 抬起鼠标前部测试 (60) |  |  |  |  | Not test
Workloading : | (Min) | Leadingtime : | (Min) | Phase :
测试准备： 1.Copy tool “AresonMouseTestProgram.exe” to the system; 2.Set test system’s Display resolution as 1920*1080, “Size of text, apps” as 125% 3.Copy the sw tool ”AresonMouseTestProgram.exe” from PA server：Z:\Test Tool and Attachement\HW_SPC_MC. 4.Open the SW tool , ensure the height of grid in tool is 1 cm（1cm for the Legion series,3cm for the regular mouse） 5.Prepare the tool(See the pic1) 测试步骤： 1. 鼠标接入系统 2.DPI setting设置为2000; 3.使用支具固定鼠标：在支具上选定一条定位线，从定位线位置开始垂直测量，抬高高度为1cm，拧紧螺丝。 4.将鼠标底部左上角接触桌面的位置对齐定位线，固定鼠标，则能使得鼠标每次抬起高度为1cm。（Legion系列为1cm，普通鼠标为3cm） 5.运行工具” AresonMouseTestProgram.exe”,勾选 “Auto Plot”; 6.以3秒10次的速度抬起支具前端， 确保每次抬起高度为1cm. 7.取5次测试结果的平均值 | [5 empty] | Not test
鼠标抬起前部测试
DUT1 | [5 empty] | Not test
DUT2 | [5 empty] | Not test
Section : | 劃線測試 (60) |  |  |  |  | Not test
Workloading : | (Min) | Leadingtime : | (Min) | Phase :
1.使用mouse test 软件; 2.左右、上下、对角快速移动画线 3.以每秒移动30cm的速度，在不同的桌面画线 （木制，玻璃，铁面，纸皮，白胶，黄色纸，浅绿纸，橙色纸等）根据项目spec定义去测试 4.检查画线不可出现打折、延迟，抖动，报告率在标准值&plusmn;10范围 5.依次切换PC的USB A/C端口，确保每个接口都测试到 6.重复步骤1-5 5次 7.关开鼠标后重复步骤1-6 5次 8.将2个鼠标接入系统，重复步骤1-7，检查报告率的变化和对鼠标功能的影响 | [5 empty] | Not test
劃線測試
玻璃 | [5 empty] | Not test
木質材料 | [5 empty] | Not test
鐵皮 | [5 empty] | Not test
黃色卡紙 | [5 empty] | Not test
綠色卡紙 | [5 empty] | Not test
橙色卡紙 | [5 empty] | Not test
黑色卡紙 | [5 empty] | Not test
白色卡紙 | [5 empty] | Not test
马尼拉纸 | [5 empty] | Not test
棉麻 | [5 empty] | Not test
丝绸 | [5 empty] | Not test
人造革 | [5 empty] | Not test
Section : | DPI按键压力测试 (60) |  |  |  |  | Not test
Workloading : | (Min) | Leadingtime : | (Min) | Phase :
压力测试
1.按下DPI键1000次，检查鼠标是否有异常 |  |  |  | 鼠标DPI功能正常，所有按键功能正常，移动鼠标没有卡顿现象 |  | Not test
Section : | DPI数值设置 (60) |  |  |  |  | Not test
Workloading : | (Min) | Leadingtime : | (Min) | Phase :
在软件设置相应的DPI数值，在设备上测试DPI是否准确 |  |  |  | 在专用DPI测试设备上显示的数值和SW设定的一致 |  | Not test
Section : | 多PC连续BT配对测试 (60) |  |  |  |  | Not test
Workloading : | (Min) | Leadingtime : | (Min) | Phase :
测试方法：BT依次和PC1~PC3配对，每连接上一台PC检查键鼠是否可用；PC3连接并测试完成后，重新关开机键鼠检查回连是否成功。 测试5台样品 | [5 empty] | Not test
Section : | 充电BT测试 (60) |  |  |  |  | Not test
Workloading : | (Min) | Leadingtime : | (Min) | Phase :
DUT与PCBT连接后，使用外接充电器（适配器）给DUT充电，经过下方操作后，检查键盘是否可以正常回连和使用 | [5 empty] | Not test
S3 | [5 empty] | Not test
S4 | [5 empty] | Not test
S5 | [5 empty] | Not test
Restart | [5 empty] | Not test
超出BT范围 | [5 empty] | Not test
Section : | 主流游戏测试 (60) |  |  |  |  | Not test
Workloading : | (Min) | Leadingtime : | (Min) | Phase :
时长为0.5h, 每种模式都要测试,每个BT通道都要测 | [5 empty] | Not test
绝地求生
宏在游戏中是否可以正常使用 | [5 empty] | Not test
灯光是否正常 | [5 empty] | Not test
测试时DPI值 | [5 empty] | Not test
是否出现异常 比如：鼠标卡顿/指针定位不精确 | [5 empty] | Not test
英雄联盟
宏在游戏中是否可以正常使用 | [5 empty] | Not test
灯光是否正常 | [5 empty] | Not test
测试时DPI值 | [5 empty] | Not test
是否出现异常 比如：鼠标卡顿/指针定位不精确 | [5 empty] | Not test
CsGo
宏在游戏中是否可以正常使用 | [5 empty] | Not test
灯光是否正常 | [5 empty] | Not test
测试时DPI值 | [5 empty] | Not test
是否出现异常 比如：鼠标卡顿/指针定位不精确 | [5 empty] | Not test
Dota-2
宏在游戏中是否可以正常使用 | [5 empty] | Not test
灯光是否正常 | [5 empty] | Not test
测试时DPI值 | [5 empty] | Not test
是否出现异常 比如：鼠标卡顿/指针定位不精确 | [5 empty] | Not test
永劫无间
宏在游戏中是否可以正常使用 | [5 empty] | Not test
灯光是否正常 | [5 empty] | Not test
测试时DPI值 | [5 empty] | Not test
是否出现异常 比如：鼠标卡顿/指针定位不精确 | [5 empty] | Not test
GTA5
宏在游戏中是否可以正常使用 | [5 empty] | Not test
灯光是否正常 | [5 empty] | Not test
测试时DPI值 | [5 empty] | Not test
是否出现异常 比如：鼠标卡顿/指针定位不精确 | [5 empty] | Not test
Wallpaper(壁纸软件)
宏在游戏中是否可以正常使用 | [5 empty] | Not test
灯光是否正常 | [5 empty] | Not test
测试时DPI值 | [5 empty] | Not test
是否出现异常 比如：鼠标卡顿/指针定位不精确 | [5 empty] | Not test
APEX
宏在游戏中是否可以正常使用 | [5 empty] | Not test
灯光是否正常 | [5 empty] | Not test
测试时DPI值 | [5 empty] | Not test
是否出现异常 比如：鼠标卡顿/指针定位不精确 | [5 empty] | Not test
无畏契约
宏在游戏中是否可以正常使用 | [5 empty] | Not test
灯光是否正常 | [5 empty] | Not test
测试时DPI值 | [5 empty] | Not test
是否出现异常 比如：鼠标卡顿/指针定位不精确 | [5 empty] | Not test
Section : | 电池测试 (60) |  |  |  |  | Not test
Workloading : | (Min) | Leadingtime : | (Min) | Phase :
电池兼容性
1.使用不同品牌的电池(金霸王、松下、南浮、GP、555、小米等)装入电池仓，进行功能测试 2.鼠标能正常工作 3.每个品牌重复步骤1-2 5次 |  |  |  | 使用不同品牌的电池，鼠标均可正常工作 |  | Not test
电池防呆
1.连接电流表，把电池反装在电池仓里， 2.检查电流表没有显示电流正常，确认是否存在短路现象 3.反装电池的情况下，不能工作、电池不能发热 4.反装时间1分钟 5.重复步骤1-4 5次 |  |  |  | 电池装反后，鼠标不能出现短路 情况，电池不能出现发热 |  | Not test
History log :
User ID |  |  | Date
Defect list :
Defect list | Title |  |  | Severity | Priority | Creator | Status